## 00-Snapshot
Snapshot for a 10-minute manager review
graph_app is the remaining SOX/graph UI core. Other GRC modules already have TypeScript MFEs. This briefing is so we start a POC with eyes open — not a request to rewrite the product.
Repo analyzed: graph_app (published as w_sox) ¦ Date: 25 Aug 2026 ¦ Audience: engineering manager ¦ Status: pre-POC briefing — not a rewrite proposal
What | Number / fact | Why a manager should care | Source
Handwritten Dart in lib/ | ~1,099 files (1,238 including generated) | This is a product, not a small module. | Confirmed file inventory 25 Aug 2026
Unit tests | 370 test files | Behavior is specified in Dart tests we must keep until cutover. | Confirmed
Functional tests | 44 suites on WDesk/Docker/Skynet | Do not spend the POC rewriting these. | Confirmed
Experience configs | 30 | Each is a WDesk screen with its own URL and OAuth scopes. | Confirmed
High-complexity areas | 12 | Keep them out of POC-1. | Tab 03
Hard blockers to a full TS SOX app | 5 (WDesk, NATS/Frugal, Audit, graph_ui, licensing) | Full cutover is a program, not a sprint. | Tab 05
TypeScript app code in graph_app today | None | There is no existing SOX TS app to 'turn on'. | Confirmed
ts-grc SOX package | None found in prior research | Universe/assessments already moved; SOX has not. | Prior research
Recommended ask in the meeting (see also tab 01-Challenge and solution)
Please approve a time-boxed POC-1 (one Unify widget in WDesk, no NATS, no table rewrite) and name owners for: (1) TS house — ts-grc vs Dart island; (2) backend GraphQL/REST coverage for SOX/graph. Please do not approve a full graph_app rewrite or a TypeScript Frugal client.

## 01-Challenge and solution
Challenges and solutions (the list to share)
Each row is one decision in Q&A form: the challenge, whether we migrate that layer, and the solution. Start with rows 1 and 2 in the meeting (Frugal, and Dart+TypeScript without moving graph_ui).
graph_app (w_sox) ¦ 26 Aug 2026 ¦ Full prose: challenges-and-solutions.md
# | Challenge (the question) | Do we migrate this layer? | Solution | In first POC?
1 | Frugal / NATS: how do we do this in TypeScript? Do we migrate Frugal, or move to something else? | No — do not port Frugal to TypeScript | Org: Frugal is not supported in TS. ts-grc already replaced it with GraphQL (Apollo) + REST (RTK Query), and polling instead of NATS pub/sub. For SOX: keep Dart GraphModule / export streams until evergreen or graph-rpc exposes GraphQL/REST. Optional: Dart calls Frugal and passes JSON/props to TS. TS never imports frugal. | No NATS. POC-2 = one REST or GraphQL call only
2 | Can Dart and TypeScript run together? Can we migrate graph_app without migrating graph_ui and other Dart packages? | Yes, coexist. No, do not migrate graph_ui first | WDesk stays Dart and still loads w_sox. TypeScript cannot import Dart packages (graph_ui, audit, w_table, w_graph_client). TS screens must not call graph_ui. Leave graph_ui/audit/w_table as Dart islands. Migrate graph_app chrome that does not need graph_ui first (Support, simple dialogs, landing-widget chrome). A full TS graph_app is not possible until those islands have a TS/MFE home. | Yes — prove coexistence. No graph_ui in the widget
3 | WDesk is still Dart. How does TypeScript load? Can we put a TS package in WDesk pubspec? | No npm in Dart pubspec. Change the integration model | Preferred: TypeScript MFE (ts-grc pattern) loaded from CDN at runtime. Fallback: Dart experience hosts a TS widget. Keep w_sox in WDesk pubspec until that screen is cut over. Do not build a standalone SOX website (loses login, nav, licensing). | Yes — one load path only
4 | OverReact UI: is there a converter, or do we rewrite? | Rewrite UI (no converter) | Manual rewrite to React 18 + @workiva/unify (same as ts-grc). Do not use raw MUI as the long-term look. One small panel in the POC, not Testing or Reports. | One Unify panel only
5 | State: Flux and Redux both exist. Can Dart and TS share one store? | No shared store | Pass props/callbacks while hybrid. When a whole experience is TS, use Redux Toolkit local to that screen (ts-grc). Do not put the store on window. Port per experience, not globally. | Presentational TS only (props)
6 | w_table / smart table: must we migrate the grid before SOX TypeScript? | No — keep Dart island | Highest UI cost. Plugins do not map 1:1. First TS screens must not include the grid. Revisit when platform has a TS grid. | Out of scope
7 | Audit is compiled into SOX. Must we migrate Audit (and other product packages) first? | No — keep Audit as a Dart island | SOX cannot pub-get a TypeScript Audit package. Same for comments, attachments, viewer, drawing, spreadsheet. Analyze audit as its own repo. Future: Audit MFE. POC must not include Audit forms. | Out of scope
8 | Login, session, and licensing: does TypeScript own auth? | No new login. Reuse shell. Relicense carefully | WDesk owns the cookie. Use shell session (ts-grc: session MFE service). Experience canUserAccessV2 stays Dart until that screen is an MFE. Any customer-facing TS UI must match Dart ability + workspace rules (SOX vs ERM vs ESG). Compliance gate, not polish. | Reuse session. Do not change access rules
9 | LaunchDarkly: new flags for TypeScript? | Replace SDK only — same flag keys | Use @workiva/grc-launch-darkly. Keep existing keys so Dart and TS dual-run. Do not invent parallel flags. | Yes — one existing flag
10 | Models (built_value, GRC YAML): convert all models first? | No bulk dump — port with each screen | No .sg.dart→TS converter. Later generate TS from the same grc_model.yaml as Dart. POC does not migrate the model layer. | Out of scope
11 | Tests: port unit and Skynet functional tests first? | Unit with each widget. Functional tests not first | Vitest + Testing Library in the same PR as the TS widget. Keep Dart unit tests until that Dart screen is deleted. Keep Puppeteer/Skynet green. Playwright later after dual-run. Do not spend the POC rewriting functional tests. | One unit test. Do not port Skynet
12 | Deploy: replace dart2js CDN / FEWS / pub package? | Add a TS artifact later — do not replace Dart deploy for the POC | POC uses current Dart CDN/FEWS. A real TS MFE gets its own pipeline (ts-grc). Dual deploy until that Dart experience is removed. Rollback = Dart. | Use existing Dart deploy
13 | i18n, analytics, logging: new event names and hardcoded strings? | Reuse Workiva TS packages; keep Next Gen analytics names | w_intl_ts + react-intl (no hardcoded UI text). Analytics: names from ANALYTICS_MIGRATION_MAPPING.md. Logging: grc-logger; TS errors must reach App Intelligence. | Optional: one log/error boundary
14 | Comments, attachments, viewer, drawing, spreadsheet: replace with generic npm libraries? | No — platform Dart/MFE islands | Dart experience keeps loading those CSS/JS assets. Do not replace w_viewer with a generic PDF viewer or the spreadsheet with a generic grid. | Out of scope
15 | Landing widgets and embeddable spreadsheets: can we remove w_sox from WDesk after one TS screen? | No — Dart keeps registering them until WDesk has an MFE contribution point | Those configs still live on w_sox. Confirm widget/embeddable MFE support before promising to drop the Dart package. | Out of scope
16 | Dart + TypeScript in the same product: how do we deploy? Do we need everything as a microservice? | No — not microservices. Frontend packaging only | MFE ≠ microservice. Backends stay as they are. POC Model A: Vite builds JS, include it in the existing w_sox/CDN tarball (same way graph_app already loads graph_app_js). Later Model B: a TS MFE is a second FEWS/CDN frontend artifact next to Dart w_sox; WDesk loads both. Do not create a K8s service per screen or a new Frugal service for TypeScript. | Model A: JS on existing Dart CDN
Meeting takeaway: (1) Do not port Frugal — replace with GraphQL/REST and keep Dart for NATS until coverage exists. (2) Yes, Dart+TS together — migrate graph_app chrome without moving graph_ui/audit/w_table. POC = one Unify widget + later one REST/GraphQL call. Deploy is not microservices: POC ships TS as JS on the existing CDN, or later as one TS MFE artifact beside w_sox.

## 01-How to use this sheet
graph_app Dart → TypeScript — manager briefing
Share this workbook before approving a POC. It lists complexity, challenges, and decisions we should settle first. Full technical write-up: graph_app/dart-ts-migration-living-analysis.md in research-and-learnings.
Repo analyzed: graph_app (published as w_sox) ¦ Date: 25 Aug 2026 ¦ Audience: engineering manager ¦ Status: pre-POC briefing — not a rewrite proposal
What to tell leadership in one paragraph
graph_app is the main IntRisk GRC (SOX) UI. Production does not run it as a standalone website — WDesk loads it as a Dart package named w_sox. A one-shot rewrite is not recommended. Other GRC modules already ship TypeScript from the ts-grc monorepo using GraphQL. This repo still owns testing, reports, data, planning, and evidence testing; those screens still talk to backends over Frugal/NATS; and WDesk cannot import a TypeScript package. Ask: approve a small POC that proves how TypeScript can live inside today's WDesk, plus one REST/GraphQL API call — not a NATS rewrite and not a full SOX rewrite.
Tab | Who it is for | What it answers | How to use in a meeting
02-Ask of manager | Manager / TPM | What we need decided before a POC | Start here. Get yes/no on the six asks.
03-Complexities | Manager + tech leads | What is hard and why (Low / Medium / High) | Show the High items; do not debate Low items in the meeting.
04-Challenges | Manager + platform partners | Confirmed problems in this repo | Use to explain why a full rewrite is unsafe.
05-Blockers and risks | Manager | What would stop or hurt the program | Blockers need a named owner before POC-2 (API).
06-Recommended POC | Manager | What we will and will not build | Approve POC-1 scope. POC-2 only after POC-1.
07-Open questions | Leads | Questions still unanswered | Assign owners; do not block POC-1 on all of these.
Evidence labels used in later tabs
Label | Meaning | How to treat it | Talking point
Confirmed | Seen in graph_app source, pubspec, tests, or CI | Treat as fact | Safe to quote
Prior research | From existing ts-grc / org TS notes, not re-opened here | Likely true; confirm with owners | Do not present as newly proven
Open | Not proven yet | Needs an owner | Do not guess in the meeting

## 02-Ask of manager
Decisions needed before we start a POC
These are the yes/no (or named-owner) asks. POC-1 can start after rows 1–3. Do not start a SOX rewrite until blockers B1–B5 have a path.
Repo analyzed: graph_app (published as w_sox) ¦ Date: 25 Aug 2026 ¦ Audience: engineering manager ¦ Status: pre-POC briefing — not a rewrite proposal
ID | Ask | Why it matters before POC | Recommended answer | If we skip this | Needed for | Manager decision (fill in)
A1 | Approve a small POC, not a rewrite of graph_app. | graph_app is ~1,100 handwritten Dart files, compiled into WDesk. A rewrite would freeze product work and still leave Audit, graph_ui, and NATS unsolved. | Yes — POC only. | Team starts a multi-quarter rewrite with no proof of WDesk + TS. | POC-1
A2 | Confirm new TypeScript follows ts-grc (React, Unify, RTK, Apollo/REST), not a new stack. | Other GRC modules already ship this way. A second stack doubles training, CI, and review load. | Yes — reuse ts-grc conventions. | Two TypeScript platforms inside GRC. | POC-1
A3 | Choose the first house for SOX TypeScript: ts-grc MFE vs TypeScript island inside Dart w_sox. | WDesk cannot pub-depend on npm. Org golden path is MFE. Hybrid TS-in-Dart is not in this repo today. | Prefer ts-grc MFE if WDesk can load it; otherwise Dart host + TS widget. | POC built in the wrong place and thrown away. | POC-1
A4 | Agree TypeScript will not call Frugal/NATS in the browser. | Org position: Frugal is not supported in TypeScript. ts-grc uses GraphQL + REST. graph_app still uses NATS for graph, GRC services, and export progress. | Yes — REST/GraphQL or Dart island for streams. | POC blocked on an unsupported API, or we build a dead-end NATS client. | POC-2
A5 | Name backend owner to confirm GraphQL/REST coverage for SOX, graph, export, dashboards. | Without this, we cannot know if ts-grc's API pattern works for this product. | Named evergreen/graph API owner this sprint. | UI POC cannot prove the data path; we only prove buttons. | POC-2
A6 | Keep Dart functional tests (Skynet) until a screen has TypeScript parity. Do not port tests first. | Largest cost after UI. Tests prove login, licensing, and WDesk still work. | Yes — dual-run later, not first. | We spend the POC rewriting tests instead of proving architecture. | All POCs
A7 | Do not migrate audit or graph_ui as part of this POC. | Both are Dart libraries compiled into SOX. Moving them first breaks current WDesk. | Analyze those repos next; leave as Dart islands for now. | Scope explodes; SOX cannot even build. | Program, not POC
A8 | Protect licensing/access parity as a compliance gate, not a polish item. | Access uses licensing abilities plus workspace type (SOX vs ERM vs ESG). Wrong gates are a product/compliance incident. | Any later TS screen must match Dart canUser rules. | Users see (or lose) screens they should not. | Before any customer-facing TS screen
Suggested meeting outcome: approve A1–A3 and A6 now; assign owners for A4–A5; park A7–A8 as program rules.

## 03-Complexities
Complexity list (graph_app)
Complexity is effort and coupling, not a reason to skip the work. High items should stay out of the first POC.
Repo analyzed: graph_app (published as w_sox) ¦ Date: 25 Aug 2026 ¦ Audience: engineering manager ¦ Status: pre-POC briefing — not a rewrite proposal
Area | Complexity | What it is today (plain language) | TypeScript approach | Related teams / repos | In first POC? | Why this complexity exists | Talking point for manager
WDesk integration (w_sox Dart package) | High | WDesk compiles w_sox into the desktop shell. TypeScript cannot be added to a Dart pubspec. | Keep Dart w_sox until a SOX MFE is registered, or embed TS inside Dart. | WDesk, wdesk_sdk | No — only prove one load path | Shell still Dart; SOX is a library, not a website. | This is the main constraint. Integration model must change before a full TS app.
UI rewrite (OverReact → React + Unify) | High | Every screen is Dart OverReact. No automated converter. ~1,100 handwritten library files. | Manual rewrite to React 18 + @workiva/unify (same as ts-grc). | Unify, graph_app | No — one small panel only | Volume plus visual parity with WDesk. | Effort is large; POC should prove one widget, not convert Testing.
Frugal + NATS APIs | High | Live graph, GRC testing, and export progress use NATS. Org does not support Frugal in TypeScript. | GraphQL/REST like ts-grc, or keep Dart for streams. Do not write a TS Frugal client. | evergreen, graph, messaging | No NATS in POC | Realtime and RPC were built on NATS, not HTTP. | API is the technical blocker, not the UI framework.
audit compiled into SOX | High | Audit screens are imported as a Dart package. SOX cannot pub-get TypeScript Audit. | Leave Audit as a Dart island or a future Audit MFE. | audit | Out of scope | One WDesk app, two products. | SOX cannot be 'fully TypeScript' while Audit stays a Dart library.
graph_ui shared library | High | Routes, graph services, and forms come from graph_ui. Migrating it first breaks Dart SOX and Audit. | Keep Dart until SOX/Audit consume a TS library or MFE. | graph_ui | Out of scope | Shared UI is a Dart package, not an MFE. | Do not start the program by rewriting graph_ui.
w_table / smart table | High | Reports, test steps, and planning use a Workiva grid plus many custom plugins. | Keep as Dart island until a platform TS grid exists. | w_table | Out of scope | Plugins do not map 1:1 to a generic grid. | Highest UI cost. Last to migrate.
Licensing and workspace access | High | Each screen checks abilities and workspace type (SOX, ERM, ESG, etc.). | Reimplement the same rules; test Dart vs TS side by side. | licensing, IAM | Not in POC-1 | Product entitlements, not just login. | Wrong gates are a compliance issue.
State: Flux and Redux both used | High | Older screens use Flux (SoxStore). Newer screens use Redux. Dart and TS cannot share one store. | Redux Toolkit per experience; pass props during hybrid. | graph_app | No shared store in POC | The app grew two state systems over years. | Do not plan one global TS store on day one.
Immutable models / codegen | High | 63 built_value models plus a Python-generated GRC YAML model. | Port models with each screen; generate TS from the same YAML later. | graph_app, backends | No bulk dump | Codegen is Dart-only; business fields live here. | No bulk 'convert all models' project.
Platform islands (comments, attachments, viewer, drawing, spreadsheet) | High | SOX loads CSS/JS from many Workiva packages. No public npm substitute. | Stay Dart/MFE islands. | DocPlat / platform UI | Out of scope | These are platform products, not SOX widgets. | Do not replace the document viewer or spreadsheet with a generic library.
Functional tests + Skynet + WDesk stack | High | 44 Puppeteer suites on a large Docker/WDesk stack. | Keep Dart tests green; Playwright later per experience. | DevOps, Skynet, WDesk | Do not port first | Tests prove the real shell, not a toy app. | Largest cost after UI. Dual-run before cutover.
Dual deploy (CDN, Docker, FEWS, pub package) | High | CI publishes a Dart pub package, CDN assets, a WDesk Docker image, and FEWS. | Add a TS artifact later; dual-run until Dart is gone. | DevOps, FEWS | POC uses existing Dart deploy | Production path is the Dart package + CDN, not a standalone SPA. | Rollback is two artifacts during hybrid.
Experience registry, routes, OAuth scopes | Medium | 30 experience configs define URLs, deferred load, scopes (sox¦r, linking, viewer, etc.). | Copy the same route segments and scopes onto any MFE. | WDesk | Must not change URLs | Deep links and shell security. | Bookmarks must keep working.
LaunchDarkly flags | Low | Same flag keys in Dart wrapper today. | Use JS/ts-grc LD packages; keep the same keys. | LaunchDarkly | Yes — one flag in POC-1 | Flags already exist; SDK is the easy part. | Easy win if we do not rename keys.
REST upgrade API (already Dio/OpenAPI) | Medium | Upgrade wizard already talks REST to graph-rpc-service, plus a live graph stream. | OpenAPI → TS client. Stream still needs another path. | graph-rpc | Possible POC-2 | REST exists; progress UX still streams. | Best API beachhead if evergreen GraphQL does not cover SOX yet.
Session / login | Low | WDesk owns login and the cookie. graph_app does not implement login. | Read shell session (ts-grc: session MFE service). No TS login page. | WDesk | Yes — reuse shell | Auth is already centralized. | Do not build a second login.
Cache and localStorage prefs | Low | In-memory SOX caches and a few browser storage keys. | Rewrite with same key names so users keep preferences. | graph_app | Not needed in POC | Local UX only. | Keep key names or users lose settings.
Count: High 12 ¦ Medium 2 ¦ Low 3 — First POC should only touch Low items plus one High integration path (WDesk load), never NATS, w_table, Audit, or graph_ui.

## 04-Challenges
Challenges (confirmed in graph_app unless noted)
A challenge is a real constraint. Complexity is how hard it is to change. Some challenges are already solved for other GRC apps in ts-grc — not yet for SOX.
Repo analyzed: graph_app (published as w_sox) ¦ Date: 25 Aug 2026 ¦ Audience: engineering manager ¦ Status: pre-POC briefing — not a rewrite proposal
Challenge | Confirmed here? | Impact if ignored | Who must help | Already solved elsewhere? | Still a SOX problem? | What we need before POC
No Dart→TypeScript converter — application code is a rewrite | Yes | Planning a 'mechanical migration' underestimates calendar time | graph_app | N/A — rewrite is the org path | Yes | Set expectation: POC is a new widget, not a translator demo
WDesk cannot depend on a TypeScript package | Yes | A TS SOX app cannot be 'pub get' into WDesk | WDesk / wdesk_sdk | ts-grc MFEs load at runtime (other modules) | Yes — w_sox is still compile-time | Pick MFE vs Dart-host path (Ask A3)
Frugal is not supported in TypeScript (org); this app still uses NATS | Yes | HTTP-only would drop live graph and export progress | evergreen / graph / messaging | ts-grc uses Apollo GraphQL + REST for other modules | Yes — SOX/graph/export coverage unknown | Named API owner (Ask A5)
Audit is compiled into SOX | Yes | SOX cannot be fully TS while Audit is a Dart library | Audit team | Not as a SOX island | Yes | Keep Audit out of POC
graph_ui is a Dart library SOX imports | Yes | Rewriting graph_ui first breaks SOX and Audit | graph_ui team | No TS library confirmed in this pass | Yes | Keep graph_ui out of POC
Flux and Redux both exist; Dart and TS stores cannot merge | Yes | Duplicate state and event bugs during hybrid | graph_app | ts-grc uses Redux Toolkit | Yes | POC is presentational (props), no shared store
w_table plugins are extensive | Yes | Reports/testing tables cannot move with the first screens | w_table / platform | Unknown TS grid | Yes | No grid in POC
Functional tests are Puppeteer + Skynet + WDesk Docker | Yes | Porting tests first burns the POC | DevOps | Playwright later (org notes) | Yes | Keep Dart tests; add test ids on any TS widget
Dual publish: pub package + CDN + Docker + FEWS | Yes | Version skew between Dart shell and TS remote | DevOps | ts-grc has independent FEWS pipelines | Yes for w_sox | POC rides existing Dart deploy
Licensing + workspace suppression (SOX vs ERM vs ESG, PBC, etc.) | Yes | Wrong users see or lose product areas | Licensing + GRC | ts-grc session/IAM patterns exist; SOX map is local | Yes | Do not change access rules in POC
Landing widgets and embeddable spreadsheets | Yes | Removing w_sox too early breaks home and embedded forms | WDesk / landing page | MFE widget contribution still unverified | Yes | Out of POC; list as program risk
analytics mid-migration (legacy + Next Gen names) | Yes | Broken product metrics | Analytics | ts-grc analytics packages exist | Yes if we emit old names | If POC sends events, use Next Gen names only
Git-pinned unpublished audit and wdesk_sdk SHAs | Yes | Platform APIs can move under SOX during the POC | Audit, WDesk SDK | N/A | Yes | Call out as schedule risk; do not block POC-1
SOX / reports / data / planning / evidence testing not in ts-grc today | Prior research + this pass | There is no existing TS SOX app to 'turn on' | ts-grc + graph_app | Universe/assessments/frameworks/requests have TS MFEs | Yes — this is the remaining core | POC creates the first SOX TS foothold
Prior notes said universe/assessments still bundle via w_sox — current pubspec does not list them | Yes (absence confirmed) | Wrong plan for removing w_sox from WDesk | WDesk registry owners | Those modules may already be MFEs | Planning risk | Confirm where they register before promising bundle-size wins

## 05-Blockers and risks
Blockers and risks
Blocker = POC-2 or a full cutover cannot succeed until this has a path. Risk = can proceed but needs a control.
Repo analyzed: graph_app (published as w_sox) ¦ Date: 25 Aug 2026 ¦ Audience: engineering manager ¦ Status: pre-POC briefing — not a rewrite proposal
ID | Type | Item | Why it hurts | Needed before | Owner to assign | Mitigation
B1 | Blocker | WDesk Dart pubspec ↔ w_sox | A TypeScript package cannot replace w_sox without an MFE (or Dart facade). | Any production TS SOX app | WDesk | Keep Dart w_sox; add MFE or hybrid island.
B2 | Blocker | No TypeScript Frugal; SOX APIs still NATS | Graph, GRC services, export status still NATS. ts-grc GraphQL may not cover them. | POC-2 and any data-heavy screen | evergreen / graph API | Inventory GraphQL/REST; poll or keep Dart streams.
B3 | Blocker | package:audit compiled in | SOX cannot be fully TS while Audit is a Dart library. | Declaring SOX 'done' in TS | Audit | Dart island or Audit MFE later.
B4 | Blocker | package:graph_ui compiled in | Same as Audit for shared graph UI. | Declaring SOX 'done' in TS | graph_ui | Dart island; analyze graph_ui next.
B5 | Blocker | Licensing + workspace access rules | Compliance incident if TS gates differ. | Any customer-facing TS screen | GRC + licensing | Golden tests Dart vs TS; no rule changes in POC.
R1 | High risk | w_table / smart table | Highest UI cost; last to move. | Reports / test-step TS | w_table | Keep grid in Dart.
R2 | High risk | Two state systems + no shared Dart/TS store | Hybrid screens disagree on data. | Any hybrid feature | graph_app | Props/callbacks only in POC.
R3 | High risk | Dual deploy artifacts | Harder rollback and version skew. | Second TS artifact | DevOps | POC uses current Dart CDN/FEWS.
R4 | High risk | Skynet functional tests | False confidence if we skip; wasted time if we port first. | Experience cutover | DevOps | Keep Dart tests green.
R5 | Medium | Analytics dual-send still in progress | Metrics drop or duplicate. | Any TS event | Analytics | Next Gen names only.
R6 | Medium | Git-pinned audit / wdesk_sdk | POC can break on unrelated SHA bumps. | Release train | Platform | Pin and communicate.
R7 | Medium | User content XSS/CSP (forms, TQ, markup) | Security regression. | Any TS form | graph_app + Infosec | React escaping; no innerHTML; shell CSP.

## 06-Recommended POC
Recommended POC (what to approve)
Goal: prove the assumptions that would kill the plan if false. Not a flagship screen. Not a NATS rewrite.
Repo analyzed: graph_app (published as w_sox) ¦ Date: 25 Aug 2026 ¦ Audience: engineering manager ¦ Status: pre-POC briefing — not a rewrite proposal
Phase | In scope | Out of scope | Must prove | Success looks like | Suggested staffing
POC-1 — first (approve now) | One presentational Unify panel in WDesk: Support tab, landing-widget chrome, or a simple dialog. Same route, same OAuth scopes, same access check. | NATS, w_table, Audit forms, test form save, reports, evidence testing, new login. | 1) Screen still registers in WDesk. 2) TS UI renders. 3) Shell session works with no TS login. 4) One LaunchDarkly flag, same key. 5) TS error is logged. 6) One unit test. 7) make serve / FEWS still works. | We know how TypeScript ships next to today's Dart SOX — in ts-grc or inside Dart — without breaking WDesk. | 1 graph_app UI engineer + WDesk/MFE consult as needed. Small, time-boxed.
POC-2 — only after POC-1 | One API call using REST or GraphQL and the shell session (upgrade REST or evergreen if SOX is covered). | Browser Frugal/NATS client. Full export streaming unless polling is agreed. | TS can read real GRC data the same way ts-grc does, without Frugal. | We know whether SOX needs new backend GraphQL/REST or can reuse evergreen. | 1 UI engineer + 1 evergreen/graph API engineer.
Do not approve as 'the POC'
Idea we should reject for the first POC | Why
Rewrite Testing (test form) in TypeScript | Highest product risk; NATS + w_table + licensing + Audit widgets.
Rewrite reports / smart table | w_table plugins are a platform problem, not a POC.
Build a TypeScript Frugal or NATS client | Org hard blocker; ts-grc already avoided this.
Standalone SOX website (no WDesk) | Loses login, nav, licensing. Not acceptable for production.
Port functional tests first | We would spend the POC on Puppeteer, not architecture.
Migrate graph_ui or audit first so SOX can 'just switch' | Breaks current Dart consumers. Analyze those repos separately.
After POC: remaining order is support/landing chrome → REST screens → testing list chrome → last: test form, reports, evidence testing, dashboards, planning.

## 07-Open questions
Open questions (assign owners)
POC-1 should not wait for all of these. Highlighted rows should have an owner before POC-2.
Repo analyzed: graph_app (published as w_sox) ¦ Date: 25 Aug 2026 ¦ Audience: engineering manager ¦ Status: pre-POC briefing — not a rewrite proposal
# | Question | Blocks POC-1? | Blocks POC-2? | Suggested owner
1 | Should SOX TypeScript live in ts-grc as an MFE, or as an island inside Dart w_sox? | Yes | Yes | WDesk + GRC leads
2 | Does grc-evergreen GraphQL (or graph-rpc REST) cover SOX testing, graph, export progress, dashboards, TQ? | No | Yes | evergreen / graph API
3 | If not, who owns new GraphQL/REST for graph NATS subjects? | No | Yes | Platform / graph
4 | Is useTsComponent / dart_ts_hmr supported for graph_app? It is not in this repo. | If we choose Dart-host path | No | WDesk SDK / org TS path
5 | Keep Audit as a Dart island, or Audit MFE first? | No | No | Audit
6 | Same question for graph_ui. | No | No | graph_ui
7 | Is there a TypeScript w_table (or successor)? | No | No | w_table
8 | What is graph_app_js, and is it already TypeScript? | No | No | graph_app_js owners
9 | Can landing-page widgets and embeddable spreadsheets be contributed from an MFE? | No | No | WDesk / landing
10 | How do we generate TS from grc_model.yaml without drifting from Dart? | No | No | graph_app
11 | Are git overrides of audit and wdesk_sdk temporary? | No | No | Audit / WDesk SDK
12 | Where do universe/assessments/frameworks/requests register now, if not in graph_app? | No | No | WDesk registry